## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I get sick | 3 | 13 | 39 | 2023-03-22 | I got a little sick so hopefully I wont geet sick again. | A | Can get extension if I get sick
Simplicity having issues | 13 | 20 | 260 | 2023-03-22 | Not using any new drivers. | O | If simplicity has issues ask TA or Instructor for help
Getting less work done next weekend during VSA retreat | 100 | 1 | 100 | 2023-04-06 |  | M | Try to get work done before and during free time.
Having a Semiconductors take home test wends-fri | 100 | 5 | 500 |  |  | M | get work done in the first half of the week
0
0
0
0
0

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100